## Worksheet 1
Date | Bulletin development/feedback
Nov 2018 | First draft of the bulletin created by producers
Nov 2019–Jan 2019 | Internal discussions between producer and intermediary team members
Jan 2019 | Feedback received from key producer team member
Feb 2019 | Internal discussion between producers and intermediaries at in-person project meeting
Draft example bulletin shared with users
Jun 2019 | Week-long workshop between producers and intermediaries focused primarily on the bulletin
Jul–Sep 2019 | Feedback from producers and intermediaries over summer after trialling daily bulletin
(not shared with users)
Sep–Nov 2019 | Multiple internal project video calls to discuss between producers and intermediaries
Nov 2019 | Week-long workshop between producers and intermediaries focused primarily on the bulletin
Nov–Dec 2019 | Bulletin template shared and discussed with users at study sites
Feb 2020 | Internal discussion between producers and intermediaries at in-person project meeting
Jun 2020 | Producer's internal discussion, approval, and sign-off
25 Jun 2020 | Project team call to agree content before sharing with users for experimental, closed trial
1 Jul 2020 | Bulletin issued daily to users in experimental, closed trial